## Sheet1
BUILDING | FACILITY | ITEM | SYSTEM | PRIORITY 1-5 | SUB-PRIORITY | ESTIMATED COST | YEAR 1 COST FY24 | YEAR 2 COST | YEAR 3 COST | YEAR 4 COST | YEAR 5 COST | COMMENT
All | All | Campus Improvements Annual fund |  | 1 | 1 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
All | All | IM&T Equipment replacement ANNUAL | IM&T | 1 | 1 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
All | St Academic | Office refresh program ANNUAL | Finishes | 1 | 1 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
All | All | Classroom Reno & furniture fund ANNUAL (McKee furn) | Finishes | 1 | 1 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
All | All | exterior caulking all campus ANNUAL | Structure | 1 | 1 | 50000 | 0 | 75000 | 75000 | 75000 | 75000
Parking | All | Parking lot maintenance ANNUAL | Parking | 1 | 1 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Site | All | sidewalk repair full campus ANNUAL | Site | 1 | 1 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
Site | All | Tree trimming & replacement | Site | 1 | 1.1 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
All | All | Security Camera replacement | Safety | 1 | 1.1 | 40000 | 40000
CC Res Halls | Aux | Replace carpet and paint | Finishes | 1 | 1.1 | 6000000 | 500000 | 500000 | 500000 | 500000 | 500000
Cand / Michener | Academic | Chiller bid overage | HVAC | 1 | 1.1 | 300000 | 300000
Gray Hall | Academic | UNC matching funds | HVAC | 1 | 1.1 | 48000 | 0 | 48000
Kohl House | Academic | Foundation leak repair, carpet, lighting | Structure | 2 | 2.1 | 15000 | 15000
Skinner | Academic | Chiller replacement (HVAC #1) | HVAC | 2 | 2.1 | 162000 | 162000
Harrison Hall | Aux | elevator soft start (Elev # 1) | Elevator | 2 | 2.2 | 40000 | 40000
University Center | St Fee | Air balance Food service area | HVAC | 2 | 2.2 | 70000 | 70000
Grounds Shop | Alll | Replace CC grounds shop | Site | 2 | 2.2 | 650000 | 650000
Carter Hall | Academic | Galv piping and main | Plumbing | 2 | 2.2 | 40000 | 40000
Ross Hall | St Academic | Relocate fire alarm system (FA #1) | Safety | 2 | 2.25 | 400000 | 400000
Tobey Kendal | Aux | Retube chiller # 1 high 2024 | HVAC | 2 | 2.3 | 80000 | 80000
Ross Hall | Academic | Cooling tower lininig & fill media | HVAC | 2 | 2.3 | 110000 | 110000
All campus | All | Panic button conversion to card system | Safety | 2 | 2.3 | 18000 | 18000
Campus Rec Center | St Fee | Elevator upgrades (Elev #2) | Elevator | 2 | 2.5 | 200000 | 200000
Butler Hancock | Academic | Wrestling AHU(HVAC #2) | HVAC | 2 | 2.5 | 85000 | 85000
University Center | St Fee | lobby ceiling & lighting replacement main level | Finishes | 2 | 2.6 | 200000 | 200000
Butler Hancock | St Academic | Repaint BH 100 | Finishes | 2 | 2.65 | 30000 | 30000
Michener Library | St Academic | Replace cooling tower fill 2024 | HVAC | 2 | 2.65 | 75000 | 75000
Lawrenson | Aux | Install CHW piping to TLC | HVAC | 2 | 2.7 | 450000 | 450000
University Center | St Fee | Dishmachine replacement | Food Service | 2 | 2.7 | 500000 | 500000
Ross Hall | Academic | Greenhouse repairs, roof panels, sun shade, | Structure | 2 | 2.7 | 100000 | 100000
Tobey Kendal | Aux | Elevator upgrades frt (Elev # 3) | Elevator | 2 | 2.7 | 230000 | 230000
Ross Hall | St Academic | Reroof 1989 wing (2023 $) | Roofing | 2 | 2.7 | 200000 | 200000
Total for FY23-24 Deferred Maintenance | [6 empty] | 5310000
Jackson Ropes | Academic | Renovate ropes course | Site | 2 | 2.71 | 385000 |  | 385000
Site | All | West campus pedestrian lighting upgrades Ongoing project Annual approx 12 poles | Site | 2 | 2.71 | 50000 |  | 50000
Site | All | Site furnishings | Site | 2 | 2.71 | 50000 |  | 50000
Frasier Hall | Academic | Frasier circle landscape | Site | 2 | 2.71 | 100000 |  | 100000
Gray Hall | Academic | Electrical upgrades IM&T UPS, EM Pwr | Electrical | 2 | 2.71 | 100000 |  | 100000
Cassidy | St Fee | Fire sprinklers & fire alarm (FA # 3 ??) | Safety | 2 | 2.75 | 500000 |  | 500000
Heat Plant | Academic | Boiler # 3 abate and demo | HVAC | 2 | 2.75 | 250000 |  | 250000
Kepner Hall | Academic | Monfort plaza masonry / conc repair | Site | 2 | 2.75 | 50000 |  | 50000 |  |  |  | conc proj??
Holmes | Aux | DHW heater replacement | Plumbing | 2 | 2.75 | 70000 |  | 70000
Michener | Academic | Window coverings 1st and 2nd | Finishes | 2 | 2.75 | 50000 |  | 50000
Butler Hancock | Academic | West entry landscape | Site | 2 | 2.75 | 40000 |  | 40000
Gray Hall | St Academic | Replace generator | Electrical | 2 | 2.75 | 500000 |  | 500000
McKee Hall | Academic | Restroom paint and partitions | Finishes | 2 | 2.8 | 200000 |  | 200000
Site | St Academic | Irrigation Michener / BH area | Site | 2 | 2.8 | 150000 |  | 150000
University Center | St Fee | Roof replacement Ballroom & 7 chiler rm (2024) (2023 $) | Roofing | 2 | 2.8 | 520000 |  | 520000
Nottingham | St Athletic | replace fire alarm ( FA #2) | Safety | 2 | 2.8 | 150000 |  | 150000
University Center | St Fee | Dock door replacement | Doors/windows | 2 | 2.8 | 50000 |  | 50000
University Center | St Fee | Pano AHU, replacement (HVAC #3) | HVAC | 2 | 2.8 | 750000 |  | 750000
Nottingham | St Athletic | Recoat west bleacher stucco wall | Site | 2 | 2.8 | 15000 |  | 15000
Site | Academic | site furnishings | Site | 2 | 2.8 | 50000 |  | 50000
Site | Site | West campus bike path repair | Site | 2 | 2.8 | 100000 |  | 100000
Campus Rec Center | St Fee | Interior paint | Finishes | 2 | 2.8 | 110000 |  | 110000
University Center | St Fee | Replace meeting room carpet | Finishes | 3 | 2.8 | 60000 |  | 60000
McKee Hall | St Academic | Corridor Carpet & replacement (1,2,3&5) and paint RR paint & partitions | Finishes | 2 | 2.85 | 242000 |  | 242000
Arlington | Aux | Fire sprinklers Attic | Safety | 2 | 2.85 | 700000 |  |  | 700000
Michener Library | Academic | CHW variable flow for Mich | HVAC | 2 | 2.9 | 525000 |  |  | 525000
Presidents House | State Admin | Repipe galv plumbing and main | Plumbing | 2 | 2.9 | 50000 |  |  | 50000
Candelaria | Academic | CHW variable flow for CB II | HVAC | 2 | 2.9 | 300000 |  |  | 300000
Site | Site | 14th and 20th Entry sign | Site | 2 | 2.9 | 135000 |  |  | 135000
McKee Hall | Academic | signage upgrades | Finishes | 2 | 2.9 | 100000 |  |  | 100000
Arlington | Aux | Caulk windows | Structure | 3 | 3 | 90000 |  |  | 90000
Ross Hall | State Admin | Reroof deck 5 North EPDM | Roofing | 3 | 3 | 361928 |  |  | 361928
University Center | St Fee | Rerof deck 4 (2028) | Roofing | 3 | 3 | 1035000 |  |  | 1035000
Arts Annex | St Academic | replace roof addition (2025) | Roofing | 3 | 3 | 165600 |  |  | 165600
Carter Hall | State Admin | fire alarm system (FA #3) | Safety | 3 | 3 | 200000 |  |  | 200000
CC Res Halls | Aux | Small flat roofs | Roofing | 3 | 3.03 | 35000 |  |  | 35000
Michener | St Academic | east storefront and thresholds repl | Doors/windows | 3 | 3.03 | 125000 |  |  | 125000
Kepner Hall | St Academic | interior sign replacement UNC std | Finishes | 3 | 3.05 | 60000 |  |  | 60000
Frasier Hall | St Academic | replace roof section 1 (2020) | Roofing | 2 | 3.1 | 1138500 |  |  | 1138500 |  |  | CM REQ??
University Center | St Fee | Meeting Room ceiling upgrades | Finishes | 2 | 3.1 | 300000 |  |  | 300000
Lawrenson | Aux | Reroof elev penthouse (2026) | Roofing | 3 | 3.15 | 34000 |  |  |  | 34000
University Center | St Fee | Atrium RTU replacement (HVAC # 4) | HVAC | 2 | 3.15 | 500000 |  |  |  | 500000
Tobey Kendal | Aux | chiller addition roof (2027) | Roofing | 3 | 3.15 | 51940 |  |  |  | 51940
Heating Plant | State Admin | Roofing replacement (2028) | Roofing | 3 | 3.15 | 230000 |  |  |  | 230000
Parking | Site | E lot mill and overlay | Parking | 3 | 3.15 | 350000 |  |  |  | 350000
Michener Library | St Academic | Carpet replacement 2nd floor | Finishes | 3 | 3.15 | 400000 |  |  |  | 400000
Carter Hall | State Admin | replace roofing (2026) | Roofing | 3 | 3.15 | 690000 |  |  |  | 690000 |  | CM Request?
Belford | Aux | foundation leaks | Structure | 3 | 3.2 | 50000 |  |  |  | 50000
Candelaria | St Academic | Tile in lower level bubbling / spalling | Finishes | 3 | 3.2 | 275000 |  |  |  | 275000
Crabbe | St Academic | Data rewire #2 | IM&T | 3 | 3.2 | 78000 |  |  |  | 78000 |  | full renewal request
Michener Library | St Academic | Carpet replacement 3rd floor | Finishes | 3 | 3.2 | 400000 |  |  |  | 400000
University Center | St Fee | Replace student activities carpet | Finishes | 3 | 3.2 | 176160 |  |  |  | 176160
Hansen Willis | Aux | Fire alarm upgrade (FA # 4) | Safety | 3 | 3.3 | 426000 |  |  |  | 426000
Site | All | PSCO CC feeder & switchgear | Utility | 3 | 3.3 | 360000 |  |  |  |  | 360000
Campus Rec Center | St Fee | Replace mondo floor in weights area | Finishes | 3 | 3.3 | 170000 |  |  |  | 170000
Lawrenson | Aux | recarpet and paint corridors | Finishes | 3 | 3.3 | 430000 |  |  |  |  | 430000
Lawrenson | Aux | elevator machine & motors upgrade (Elev # 4) | Elevators | 3 | 3.3 | 400000 |  |  |  |  | 400000
Frasier | Academic | Theater chiller replacement (HVAC #4) | HVAC | 3 | 3.3 | 143000 |  |  |  |  | 143000
Ross Hall | St Academic | 2002 addition replace EPDM roofing (2027) | Roofing | 3 | 3.35 | 500000 |  |  |  |  | 500000
Gray Hall | St Academic | replace exterior water main | Site | 3 | 3.35 | 60000 |  |  |  |  | 60000
University Center | St Fee | Replace computer commons carpet | Finishes | 3 | 3.35 | 40000 |  |  |  |  | 40000
Site | All | Replace / rehab CC main N-S sanitary sewer | Utility | 3 | 3.35 | 600000 |  |  |  |  | 600000
Patton House | St Academic | Replace windows | Doors/Windows | 3 | 3.4 | 80000 |  |  |  |  | 80000
Roudebush Cottage | St Academic | window replacement | Doors/Windows | 3 | 3.4 | 60000 |  |  |  |  | 60000
Davis House | St Academic | replace windows | Doors/Windows | 3 | 3.4 | 80000 |  |  |  |  | 80000
Gray Hall | St Academic | replace exterior sewer main | Site | 3 | 3.4 | 75000 |  |  |  |  | 75000
CC Res Halls | Aux | Replace ASA lock cylinders phased | Doors/Windows | 3 | 3.4 | 500000 |  |  |  |  | 500000
Lawrenson | Aux | Apt flooring repl 16-17 LVT | Finishes | 3 | 3.4 | 230000 |  |  |  |  | 230000
Parking | All | West 1/2 J lot overlay | Parking | 3 | 3.4 | 500000 |  |  |  |  | 500000
Turner | Aux | Elevator drive upgrades (Elev # 5) | Elevators | 3 | 3.41 | 100000 |  |  |  |  | 100000
Garden Theater | St Academic | painting interior and exterior | Finishes | 3 | 3.5 | 30000 |  |  |  |  | 30000
Crabbe | St Academic | caulk | Structure | 3 | 3.5 | 50000 |  |  |  |  | 50000 | full renewal request
Gray Hall | St Academic | Tuck point masonry & caulk | Structure | 3 | 3.5 | 22000 |  |  |  |  | 22000
Nottingham | St Athletic | caulk all | Structure | 3 | 3.5 | 25000 |  |  |  |  | 25000
Presidents House | State Admin | repair / replace gutters and downspouts | Roofing | 3 | 3.5 | 10000 |  |  |  |  | 10000
Butler Hancock | St Academic | Wrestling add roofing (2026) | Roofing | 3 | 3.5 | 216000 |  |  |  |  | 216000
Carter Hall | State Admin | Tuck point masonry & caulk | Structure | 3 | 3.6 | 75000
Michener Library | St Academic | exterior caulking | Structure | 3 | 3.6 | 150000
Michener Library | St Academic | Elevator modernization gearless | Elevators | 3 | 3.6 | 450000
Michener Library | St Academic | Roof replacement | Roofing | 3 | 3.7 | 1900000 | [5 empty] | CM Request
Butler Hancock | St Academic | replace Mondo floor | Finishes | 3 | 3.7 | 2191976 | [5 empty] | CM Req
Heating Plant | State Admin | exterior caulking | Structure | 3 | 3.7 | 35000
Michener Library | St Academic | Need to repair and paint some exterior precast panels to prevent additional rust. | Structure | 3 | 3.7 | 40000
Patton House | St Academic | Replace garage door | Doors/Windows | 3 | 3.7 | 3500
McKee Hall | St Academic | Electrical switchgear & Trans replacement | Electrical | 3 | 3.8 | 1000000 | [5 empty] | CM request
Kepner Hall | St Academic | Data rewire #4 | IM&T | 3 | 3.8 | 65000 |  |  | 65000
Nottingham Wesst | St Academic | Reroof sloped roofs (2030) | Roofing | 3 | 3.8 | 15000
Kepner Hall | St Academic | Milne auditorium drape replacement | Finishes | 3 | 3.8 | 30000
Kepner Hall | St Academic | auditorium seating replacement | Finishes | 3 | 3.8 | 90000
Kepner Hall | St Academic | Milne carpet replacement | Finishes | 3 | 3.8 | 20000
Frasier Music Tech | St Academic | Music Tech wing paint | Finishes | 3 | 3.8 | 30000
Garden Theater | St Academic | Upgrade elec panel and rewire | Electrical | 3 | 3.8 | 30000
Garden Theater | St Academic | Repair cracked glass block and paint frames | Structure | 3 | 3.8 | 5500
Harrison Hall | Aux | Reoplace LTHW ht exch | HVAC | 3 | 3.8 | 125000
Kepner Hall | St Academic | Replace corridor carpet | Finishes | 3 | 3.8 | 100000
Michener Library | St Academic | Patch and repair drywall in basement and lower level corridors | Finishes | 3 | 3.8 | 45000
Presidents House | State Admin | Replace ext. doors and windows (1988) | Doors/Windows | 3 | 3.8 | 159800
University Center | St Fee | Install fire sprinkler system (insurance) | Safety | 3 | 3.8 | 800000
Warren | Aux | poor drainage, some cracks and leakage | Structure | 3 | 3.8 | 20000
Warren | Aux | need to caulk all of exterior | Structure | 3 | 3.8 | 5000
Warren | Aux | need some masonry tuck pointing and repair | Structure | 3 | 3.8 | 2500
Young House | St Academic | repipe entire building | Plumbing | 3 | 3.8 | 25000
Crabbe | St Academic | Repl 103 ext door & frame | Doors/Windows | 3 | 3.9 | 10000 | [5 empty] | full renewal request
Crabbe | St Academic | repair exterior walls water damage. Patch and repair plaster | Finishes | 3 | 3.9 | 75000 | [5 empty] | full renewal request
Crabbe | St Academic | replace steam producer | HVAC | 3 | 3.9 | 104000 | [5 empty] | full renewal request
Crabbe | St Academic | Repair downspouts and soffit - repaint | Roofing | 3 | 3.9 | 50000 | [5 empty] | full renewal request
Crabbe | St Academic | electrical upgrade (State renewal request) | Electrical | 3 | 3.9 | 1000000 | [5 empty] | full renewal request
Crabbe | St Academic | Replace original piping system, galvanized water mains, original fixtures | Plumbing | 3 | 3.9 | 45000 | [5 empty] | full renewal request
Crabbe | St Academic | replace ceiling systems | Finishes | 3 | 3.9 | 135000 | [5 empty] | full renewal request
Crabbe | St Academic | replace carpet | Finishes | 3 | 3.9 | 150000 | [5 empty] | full renewal request
Crabbe | St Academic | repaint interior walls | Finishes | 3 | 3.9 | 195000 | [5 empty] | full renewal request
Crabbe | St Academic | Upgrade heating system and controls | HVAC | 3 | 3.9 | 1400000 | [5 empty] | full renewal request
Crabbe | St Academic | install building automation system | HVAC | 3 | 3.9 | 40000 | [5 empty] | full renewal request
Crabbe | St Academic | replace widow coverings | Finishes | 3 | 3.9 | 50000 | [5 empty] | full renewal request
Crabbe | St Academic | Replace interior door hardware | Doors/Windows | 3 | 3.9 | 85000 | [5 empty] | full renewal request
Crabbe | St Academic | modernize elevator | Elevators | 3 | 3.9 | 150000 | [5 empty] | full renewal request
Gunter Hall | St Academic | Chiller replacement (2028) | HVAC | 3 | 3.9 | 450000 | [5 empty] | CM Request
University Center | St Fee | replace floors drains and piping in kitchen | Plumbing | 3 | 3.9 | 30000
University Center | St Fee | Abs chiller replacement | HVAC | 3 | 3.9 | 1500000
Young House | St Academic | repaint exterior | Structure | 3 | 3.9 | 40000
Kepner Hall | St Academic | Roof replacement (2028) | Roofing | 3 | 3.9 | 440000
Tobey Kendal | Aux | replace steam producer | HVAC | 4 | 4 | 135000
Harrison Hall | Aux | elevator modernization 1-4 | Elevators | 4 | 4 | 625000
BH Fields Softball | St Academic | Improve drainage in dugouts | Site | 4 | 4 | 22000
University Center | St Fee | Replace student activities ceiling & ltg | Finishes | 4 | 4 | 264500
Garden Theater | St Academic | Repair concrete floor | Structure | 4 | 4 | 15000
Candelaria | St Academic | replace window gasket system | Doors/Windows | 4 | 4 | 65000
McKee Hall | St Academic | Replace gaskets in the window system | Doors/Windows | 4 | 4 | 45000
Kepner Hall | St Academic | Repair stucco coat on exterior planters, ramp and foundation walls | Site | 4 | 4 | 10000
Site | All | Replace K lot lighting | Site | 4 | 4 | 149040
Turner | Aux | repair retaining gaskets on large 1st floor window systems | Doors/Windows | 4 | 4 | 40000
Kepner Hall | St Academic | Need to refinish window interiors | Finishes | 4 | 4 | 35000
Site | All | Repair benches in stone hinge north of Gunter | Site | 4 | 4 | 12000
Turner | Aux | replace bollard lights | site | 4 | 4 | 50000
University Center | St Fee | secondary distribution system needs to be upgraded - full capacity. (service is fine) | Electrical | 4 | 4 | 450000
University Center | St Fee | Replace remaining exterior doors | Doors/Windows | 4 | 4 | 150000
Guggenheim | St Academic | Replace VCT flooring | Finishes | 4 | 4 | 56073
University Center | St Fee | Replace hood and hood FP systems | Safety | 4 | 4 | 155000
Arts Annex | St Academic | Interior paint | Finishes | 4 | 4 | 30000
Belford | Aux | DHW tank lining | Plumbing | 4 | 4 | 2500
Brown Hall | Aux | DHW tank lining | Plumbing | 4 | 4 | 2500
Butler Hancock | St Academic | Exterior caulking | Structure | 4 | 4 | 40000
Butler Hancock | St Academic | interior painting | Finishes | 4 | 4 | 90000
Butler Hancock | St Academic | elevator modernization | Elevators | 4 | 4 | 150000
Butler Hancock Field Bldg | St Athletic | Interior finishes | Finishes | 4 | 4 | 22000
Campus Rec Center | St Fee | Aux gym roof (2031) | Roofing | 4 | 4 | 210000
Campus Rec Center | St Fee | Replace stair tiles | Finishes | 4 | 4 | 41000
Cancer Rehab Center | St Academic | Roof replacement (2028) | Roofing | 4 | 4 | 85000
Candelaria | St Academic | Repaint stair handrails | Finishes | 4 | 4 | 7500
Candelaria | St Academic | Replace concealed grid ceilings - offices | Finishes | 4 | 4 | 200000
Candelaria | St Academic | interior painting | Finishes | 4 | 4 | 200000
Candelaria | St Academic | elevator modernization | Elevators | 4 | 4 | 100000
Carter Hall | State Admin | refinish interior doors | Finishes | 4 | 4 | 50000
Carter Hall | State Admin | foundation dry zone | Site | 4 | 4 | 75000
Carter Hall | State Admin | electrical upgrade capitity OK, dist issue | Electrical | 4 | 4 | 550000
Decker | Aux | DHW tank lining (2023) | Plumbing | 4 | 4 | 6000
Frasier Music Tech | St Academic | caulking (2028) | Structure | 4 | 4 | 15000
Garden Theater | St Academic | Tuck point masonry | Structure | 4 | 4 | 9000
Garden Theater | St Academic | Upgrade lighting system to theater quality | Electrical | 4 | 4 | 75000
Gordon | Aux | repair stucco | Structure | 4 | 4 | 10000
Gordon | Aux | DHW tank lining | Plumbing | 4 | 4 | 15000
Gray Hall | St Academic | Recarpet basement | Finishes | 4 | 4 | 25000
Gray Hall | St Academic | replace ceilings in basement rooms | Finishes | 4 | 4 | 35000
Guggenheim | St Academic | interior paint | Finishes | 4 | 4 | 50000
Guggenheim | St Academic | masonry pointing | Structure | 4 | 4 | 20000
Gunter Hall | St Academic | Rewire data closet #4 | IM&T | 4 | 4 | 75000
Gunter Hall | St Academic | Interior paint | Finishes | 4 | 4 | 125000
Gunter Hall | St Academic | paint ext handrails | Site | 4 | 4 | 2500
Hansen Willis | Aux | DHW tank lining | Plumbing | 4 | 4 | 15000
Harrison Hall | Aux | Upgrade controls on AHU's | HVAC | 4 | 4 | 25000
Holmes Dining | Aux | Interior painting | Finishes | 4 | 4 | 70000
Holmes Dining | Aux | EPDM roof replacement (2029) | Roofing | 4 | 4 | 400000
Holmes Dining | Aux | Replace tile flooring | Finishes | 4 | 4 | 244200
Jackson Baseball | St Athletic | paint team building exterior | Structure | 4 | 4 | 25000
Jackson Soccer | St Athletic | interior finishes | Finishes | 4 | 4 | 32000
Kepner Hall | St Academic | HVAC upgrades | HVAC | 4 | 4 | 1000000
Kepner Hall | St Academic | Replace building transformer | Electrical | 4 | 4 | 155000
Lawrenson | Aux | need to replace isolation valves for FCU's | HVAC | 4 | 4 | 60000
Lawrenson | Aux | re-line DHW tanks | Plumbing | 4 | 4 | 30000
Lawrenson | Aux | renovate kitchens A - F (2015 est) | Finishes | 4 | 4 | 1976586
Lawrenson | Aux | Chiller replacement (2027) | HVAC | 4 | 4 | 450000
McKee Hall | St Academic | Replace lecture hall seating | Finishes | 4 | 4 | 600000
McKee Hall | St Academic | repair stair treads | Finishes | 4 | 4 | 80000
McKee Hall | St Academic | Replace toilet partitions | Finishes | 4 | 4 | 80000
McKee Hall | St Academic | Replace building transformer | Electrical | 4 | 4 | 350000
Michener Library | St Academic | replace window coverings | Finishes | 4 | 4 | 60000
Michener Library | St Academic | Repaint doors and frames on lower level | Finishes | 4 | 4 | 50000
Michener Library | St Academic | install vestibules at exterior entries | Doors/Windows | 4 | 4 | 150000
Michener Library | St Academic | replace spandrel glass at AHUs | Doors/Windows | 4 | 4 | 85000
Michener Library | St Academic | main electrical switchgear replacement | Electrical | 4 | 4 | 300000
Nottingham East | St Athletic | interior finishes | Finishes | 4 | 4 | 25000
Nottingham Storage | St Athletic | replace roofing (2026) | Roofing | 4 | 4 | 10000
Old Man Mountain | Aux | Lower bunk - roof | Roofing | 4 | 4 | 7000
Old Man Mountain | Aux | shower - paint | Finishes | 4 | 4 | 4000
Old Man Mountain | Aux | shower - roof | Roofing | 4 | 4 | 7000
Old Man Mountain | Aux | shower - doors | Finishes | 4 | 4 | 3000
Old Man Mountain | Aux | Main - ext paint | Finishes | 4 | 4 | 15000
Old Man Mountain | Aux | Main - tuck point | Structure | 4 | 4 | 3000
Parking | All | BL access drive paving | Parking | 4 | 4 | 350000
Parking | All | Replace bases & wiring for L&M lights | Site | 4 | 4 | 179000
Parsons Hall | State Admin | interior finishes | Finishes | 4 | 4 | 45000
Ross Hall | St Academic | caulking | Structure | 4 | 4 | 85000
Ross Hall | St Academic | Courtyard noise screening | HVAC | 4 | 4 | 50000
Ross Hall | St Academic | Replace chiller (2028) | HVAC | 4 | 4 | 1600000 | [5 empty] | CM Request
Ross Hall | St Academic | Animal facility caulk exterior | Structure | 4 | 4 | 15000
Roudebush Cottage | St Academic | Interior finishes | Finishes | 4 | 4 | 30000
Sabin Hall | Aux | reline DHW tank | Plumbing | 4 | 4 | 6000
Scott Wilcoxen | St Academic | interior finishes | Finishes | 4 | 4 | 25000
Site | All | replace west campus pedestrain lighting | Site | 4 | 4 | 350000
Site | All | replace central campus pedestrain lighting | Site | 4 | 4 | 350000
Site | All | Combine BFP's for irrigation | Utility | 4 | 4 | 50000
Skinner Music Library | St Academic | interior paint | Finishes | 4 | 4 | 50000
Skinner Music Library | St Academic | foundation dry zone | Site | 4 | 4 | 60000
Snyder | Aux | reline DHW tank | Plumbing | 4 | 4 | 6000
Tobey Kendal | Aux | Chiller replacement (2027) 1 | HVAC | 4 | 4 | 500000
Tobey Kendel | Aux | reline DHW tank | Plumbing | 4 | 4 | 15000
Turner | Aux | replace windows | Doors/Windows | 4 | 4 | 1573270
Turner | Aux | Roof replacement elev penthouse | Roofing | 4 | 4 | 10000
Warren | Aux | need to replace galvanized water lines | Plumbing | 4 | 4 | 20000
Wiebking | Aux | need to repair stucco cracks. Poor repair previously | Structure | 4 | 4 | 35000
Wilson | Aux | need to repair stucco cracks | Structure | 4 | 4 | 35000
Young House | St Academic | prep and paint interior doors | Finishes | 4 | 4 | 5000
Young House | St Academic | repair interior plaster walls and ceiling cracks | Finishes | 4 | 4 | 10000
Candelaria | St Academic | replace plaza lights west side | Electrical | 4 | 4.1 | 150000
Crabbe | St Academic | foundation dry zone | Site | 4 | 4.1 | 75000 | [5 empty] | full renewal request
Frasier Music Tech | St Academic | MTRC dry zone plantings | Site | 4 | 4.1 | 40000
McKee Hall | St Academic | Replace interior P/L doors | Doors/Windows | 4 | 4.1 | 500000
Site | All | Reinforce tunnel top from Carter to Fac. Apt. # 1 w/ C and screw jacks | Site | 4 | 4.1 | 50000 | [5 empty] | CM request?
Site | All | Extend irrigation main on central campus academic area in conjunction with City non pot project | Utility | 4 | 4.1 | 100000
Carter Hall | State Admin | elevator modernization jack repl, cab interior upgrade, roller guides | Elevators | 4 | 4.2 | 125000
University Center | St Fee | elevator modernization cab interiors | Elevators | 4 | 4.2 | 80000
Wiebking | Aux | elevator modernization controller | Elevators | 4 | 4.2 | 120000
Wilson | Aux | elevator modernization controller | Elevators | 4 | 4.2 | 120000
Harrison Hall | Aux | Need to replace windows - Single pane | Doors/Windows | 4 | 4.3 | 1650000
Harrison Hall | Aux | Glass and aluminum doors need to be replaced | Doors/Windows | 4 | 4.3 | 220000
Arlington | Aux | Replace sloped roofs (2024/2025) | Roofing | 4 | 4.5 | [6 empty] | with Struct??
Frasier Hall | St Academic | replace steam producer | HVAC | 4 | 4.5 | 200000 | [5 empty] | full renewal request
Frasier Hall | St Academic | elevator modernization | Elevators | 4 | 4.5 | 350000 | [5 empty] | full renewal request
Frasier Hall | St Academic | Data rewire #1 | IM&T | 4 | 4.5 | 250000 | [5 empty] | full renewal request
Frasier Hall | St Academic | fire alarm upgrade for improved coverage # 3 | Safety | 4 | 4.5 | 225000 | [5 empty] | full renewal request
Frasier Hall | St Academic | Upgrade control system full building | HVAC | 4 | 4.5 | 300000 | [5 empty] | full renewal request
Frasier Hall | St Academic | Mech & elec upgrades full building | HVAC | 4 | 4.5 | 8000000 | [5 empty] | full renewal request
Frasier Hall | St Academic | Replace ceilings full building | Finishes | 4 | 4.5 | 650000 | [5 empty] | full renewal request
Frasier Hall | St Academic | refinish doors and frames | Doors/Windows | 4 | 4.5 | 600000 | [5 empty] | full renewal request
Frasier Hall | St Academic | repair hardware or replace | Doors/Windows | 4 | 4.5 | 500000 | [5 empty] | full renewal request
Frasier Hall | St Academic | tuckpoint and caulk exterior walls | Structure | 4 | 4.5 | 156000 | [5 empty] | full renewal request
Frasier Hall | St Academic | Replace carpet & VCT | Finishes | 4 | 4.5 | 250000 | [5 empty] | full renewal request
Campus Rec Center | St Fee | Relief fans for 2 & 3 court gyms | HVAC | 4 | 4.6 | 75000
Arlington | Aux | Roof structure repair and roofing | Structure
Holmes Hall | Aux | DHW heater replacement | Plumbing | 3
Michener Library | Academic | replace head on 2nd heat exchanger | HVAC | 3 |  | 50000
Heating Plant | Academic | Abate and demo boiler # 3 | HVAC | 3
Butler Hancock | Academic | Pool AHU sound screen | HVAC | 3
University Center | St Fee | North site landscaping with City | Site | 3
Nottingham | Academic | track resurface (2027) | Site | 3
Sports Fields | Academic | relamp to LED | Electrical